## Sheet1
Oh, RATS! Final Year Project Gantt Plan
Working plan from October 2026 to March 2027
Task | Start Date | Notes / Deliverable | Status
Confirm project scope and success criteria | 2026-10-01 | Confirm physical game deliverables, digital companion role, and what counts as a successful final outcome. | In progress
Research board game mechanics and hybrid interactions | 2026-10-05 | Research movement, combat, traps, accessibility, hybrid board games and physical-to-digital interactions. | In progress
Develop Svelte digital companion core | 2026-10-05 | Build on the existing QR-to-trap PoC; develop a mobile-friendly interface and core game-state features. | In progress
Finish story and gameplay overview | 2026-10-12 | Write the premise, turn sequence, win conditions, traps, encounters and mechanics still to be decided. | In progress
Review technical direction with supervisor | 2026-10-12 | Discuss Svelte/JavaScript, QR fallback, NFC feasibility and realistic scope. | Not started
Investigate NFC and physical to digital options | 2026-10-12 | Research and develop a small proof of concept using a camera to detect the positions of physical Rat and Cat pieces on the board. Investigate whether the detected positions can be sent to the Svelte application and used to trigger game events. Evaluate the accuracy, reliability and technical limitations of camera based tracking. If successful, explore integrating it into the digital companion; otherwise, retain the QR-based solution as a fallback. | In progress
Document process, research and evaluation | 2026-10-12 | Keep research, screenshots, development notes, testing evidence, limitations and reflections up to date throughout. | In progress
Define core rules and win conditions | 2026-10-19 | Set player roles, movement, winning conditions, health, trap placement and basic combat. | Not started
Sketch board layout and room/tile routes | 2026-10-26 | Plan house layout, room connections, tile system, kitchen/fridge objective and shortcuts. | Not started
Research visual styles and create moodboard | 2026-11-02 | Gather references for Rat/Cat characters, house environments, cards and a playful cartoon visual style. | Not started
Develop visual identity and character concepts | 2026-11-09 | Create Rat and Cat concepts, colour palette, typography and component style. | Not started
Design first board layout | 2026-11-09 | Create a first board map showing rooms, tiles, routes, starting positions and fridge goal. | Not started
Design first cards, traps and tokens | 2026-11-16 | Create draft card types, trap concepts, tokens and component layouts. | Not started
Build a paper/cardboard gameplay prototype | 2026-11-23 | Make a low cost prototype to test movement, turns, routes and the win condition. | Not started
Test the basic gameplay loop | 2026-12-01 | Play through a sample game and identify confusing or unbalanced rules. | Not started
Plan digital companion interface | 2026-12-01 | Sketch mobile screens for character health, component information and game-event feedback. | Not started
Revise game rules and component designs | 2026-12-07 | Use prototype findings to refine movement, traps, combat ideas and the board layout. | Not started
Create initial 2D game assets | 2026-12-07 | Develop the first usable artwork for characters, cards, traps, tiles and other components. | Not started
Implement core digital game-state interactions | 2027-01-04 | Build a manageable feature such as recording a move, identifying a component or updating health. | Not started
Refine board and component dimensions | 2027-01-04 | Set practical sizes for the board, tiles, cards and miniatures before final production. | Not started
3D model selected characters or components | 2027-01-11 | Create 3D models for selected pieces or traps; prioritise components needed for the final game. | Not started
Build a more complete playable prototype | 2027-01-18 | Combine the revised board, components, cards and current rules into a fuller game. | Not started
Print and assemble first physical components | 2027-01-25 | Test printing, scale, stability and usability, and adjust models if needed. | Not started
Playtest and refine core gameplay | 2027-01-25 | Run playtests, record issues, refine rules and balance. Check ethics requirements before formal external testing. | Not started
Improve digital companion interface and feedback | 2027-02-01 | Make the interface clearer on mobile and improve messages for traps, health and other implemented actions. | Not started
Integrate physical prototype and digital companion | 2027-02-08 | Test that the chosen physical to digital interaction fits naturally into a game turn. | Not started
Finalise board, cards, traps and instructions | 2027-02-08 | Prepare the main physical components and clear instructions for a complete play session. | Not started
Conduct full game playtesting | 2027-02-15 | Test setup to finish gameplay and identify any major problems or unclear rules. | Not started
Fix important gameplay and technical issues | 2027-02-22 | Resolve high priority issues and simplify features that threaten completion. | Not started
Photograph and record the final prototype | 2027-03-01 | Capture the board, components, gameplay and digital interaction for the portfolio and presentation. | Not started
Final polish and presentation preparation | 2027-03-01 | Prepare final files, demonstration, portfolio, handover information and presentation. | Not started
Final checks and submission | 2027-03-08 | Check all deliverables, organise project files and submit by the confirmed deadline. | Not started